PROJECT PROPOSAL Rafiq Smart Tourism Companion for Egypt DEPI – Digital Egypt Pioneers Initiative ¦ Graduation Project 2026

# 1. Project Overview

Project Title:

Rafiq– Smart Tourism Companion for Egypt

Objective:

To build a smart web-based platform that acts as a digital companion for tourists in Egypt, helping them plan trips, discover authentic experiences, avoid scams, and access emergency support — thereby improving Egypt's tourism image globally. The platform also empowers licensed tour guides to find job opportunities and enables tourists to communicate directly with them through an integrated marketplace and chat system.

Description:

Rafiq is a human-centered tourism platform that combines culture, safety, and technology. It provides:

- A smart trip planner tailored to budget, interests, and trip duration.

- A rich database of famous landmarks and authentic local places with cultural tips.

- A marketplace for verified tour guides with ratings, reviews, and direct booking.

- An anti-scam assistant with fair-price indicators and city-specific warnings.

- An emergency companion with one-click access to police, hospitals, and embassies.

- Smart AI features: review summarization, route optimization, and audio guides.

# 2. Objectives

The primary objectives of Rafiq are:

- Provide tourists with a single trusted platform covering planning, exploration, safety, and emergency support.

- Reduce tourist confusion and vulnerability to scams by offering transparent, verified information.

- Promote authentic Egyptian cultural experiences alongside well-known commercial landmarks.

- Empower licensed tour guides with a fair, transparent digital marketplace.

- Improve accessibility for tourists with disabilities through dedicated accessibility modes.

- Leverage AI and geolocation technologies to deliver smart, context-aware recommendations.

- Support Arabic and English to serve both international and local users.

- Contribute positively to Egypt's digital tourism transformation and global reputation.

# 3. Project Scope

In Scope:

- Web-based platform (desktop + mobile-responsive) — no native mobile app.

- All 8 core modules: Trip Planner, Places Explorer, Guide Marketplace, Anti-Scam Assistant, Emergency Companion, Route With Soul, Smart Audio Guide, Memory Map.

- Admin dashboard to manage places, guides, and reviews.

- Bilingual interface (English & Arabic).

- Basic AI integrations: review summarization and route optimization via OpenAI API.

- Real-time guide chat using Socket.io.

Out of Scope:

- Native iOS / Android mobile applications.

- Payment gateway integration (booking is confirmed via chat — payment handled offline).

- Full offline mode.

- Third-party travel agency partnerships.

# 4. Team Members & Responsibilities

| 1 | Eman | Full-Stack Developer – Backend & Frontend Integration |
| --- | --- | --- |
| 2 | Basmala | Frontend Developer – Pages, Components & Maps UI |
| 3 | Gerges | UI/UX Designer – Wireframes, Prototypes & Design System |
| 4 | Mahmoud | Frontend Developer – Marketplace, Dashboard & Admin UI |
| 5 | Mehrael | Backend Developer – APIs, AI Integration & Security |
| 6 | Kirolos | QA & Documentation – Testing, API Docs & Project Report |

# 5. System Architecture & Tech Stack

Rafiq follows a client-server architecture with a React single-page application (SPA) on the frontend, a Node.js/Express REST API on the backend, and MongoDB Atlas as the primary database. Real-time communication is handled via Socket.io, and AI capabilities are provided through the OpenAI API.

| Layer | Technologies |
| --- | --- |
| Frontend | React.js, Bootstrap 5, React Router, Redux Toolkit |
| Backend | Node.js, Express.js, REST API |
| Database | MongoDB (Atlas), Mongoose ODM |
| Auth | JWT, bcrypt, Role-based Access Control |
| AI / Smart Features | OpenAI API (review summarization, route optimization) |
| Maps & Geo | Google Maps API / Leaflet.js |
| Real-time | Socket.io (guide chat) |
| File Storage | Cloudinary (guide photos, place images) |
| Dev Tools | Git & GitHub, VS Code, Postman, Figma, MongoDB Compass |
| Deployment | Vercel (frontend), Render / Railway (backend) |

Architecture Diagram (High Level):

- Client Layer: React SPA (Bootstrap 5, React Router, Redux) → served via Vercel CDN

- API Layer: Express.js REST API running on Node.js → deployed on Render

- Data Layer: MongoDB Atlas (cloud-hosted) + Cloudinary (media storage)

- External Services: Google Maps API, OpenAI API, Socket.io (real-time)

- Auth: JWT tokens + bcrypt password hashing + RBAC (Tourist / Guide / Admin roles)

# 6. Methodology

The team will follow an Agile development methodology with weekly sprints, aligned with the project timeline from February to June 2026. Each sprint will include:

- Sprint Planning – divide features into tasks and assign to team members.

- Daily async stand-ups – progress updates via WhatsApp/Discord group.

- Weekly supervisor check-ins – demo of completed features, collect feedback.

- Sprint Review & Retrospective – review deliverables and adjust the plan.

Version control is managed through Git & GitHub with a feature-branch workflow. All code is reviewed via Pull Requests before merging to the main branch.

# 7. Project Timeline  (February – June 2026)

| Period | Tasks & Responsibilities | Deliverables |
| --- | --- | --- |
| Week 1 (Feb 1–7) | - Gerges – Create wireframes in Figma for all main pages (Home, Planner, Explorer, Marketplace) - Eman – Initialize Node.js/Express project, connect MongoDB Atlas, define folder structure - Mehrael – Research places data sources, scam patterns per city; set up backend skeleton - Mahmoud – Set up React project, Bootstrap layout, routing structure, component skeleton - Basmala – Define homepage layout and navigation flow in collaboration with Gerges - Kirls – Write project documentation plan, set up GitHub repo and branching strategy | - GitHub repository initialized with branching strategy - Figma low-fidelity wireframes for all screens - Database schema draft (Places, Users, Guides, Reviews) |
| Week 2 (Feb 8–14) | - Gerges – Finalize high-fidelity Figma mockups and design system (colors, typography, components) - Eman – Build Auth API (register/login/JWT), User model, role-based access control - Mehrael – Places model + CRUD API endpoints; seed initial places data - Mahmoud – Homepage + Navbar + Auth pages (Login/Register) using Bootstrap - Basmala – Places Explorer page: static UI with cards and filter layout - Kirls – Set up Postman collection, document all API endpoints planned so far | - Working Auth API (tested in Postman) - React app running with routing and Bootstrap layout - Places API (GET all, GET by ID, POST) |
| Week 3 (Feb 15–21) | - Gerges – Design Trip Planner UI, Places cards, cultural tips modal, and map view layout - Eman – Trip Planner full-stack: form + budget/interest filters + geo-sort algorithm + cost estimate - Mehrael – Guide model + Marketplace API (list, filter, book) + Emergency Companion data - Mahmoud – Places Explorer: dynamic cards fetched from API, search, filters, detail page - Basmala – Trip Planner frontend: connect form to API, display results list and map pins - Kirls – QA: test Trip Planner and Places Explorer flows; log bugs on GitHub Issues | - Trip Planner end-to-end connected - Places Explorer fetching live data - Guides Marketplace API ready |
| Week 4 (Feb 22–28) | - Gerges – Design Guide Marketplace pages, booking flow, in-app chat interface - Eman – Booking API + availability calendar logic + Socket.io chat backend setup - Mehrael – Anti-Scam Assistant backend: price-warning logic, city scam data API - Mahmoud – Guide Marketplace page: listing, filter, booking form, guide profile page - Basmala – In-app chat UI + booking confirmation and success pages - Kirls – QA: test booking flow and chat; update API documentation in Postman | - Guide booking flow end-to-end - In-app chat prototype working - Anti-scam assistant API ready |
| Week 5 (Mar 1–7) | - Gerges – Design Audio Guide, Route With Soul, Memory Map, and Accessibility Mode UI - Eman – Smart Audio Guide full-stack: proximity trigger logic + audio content API - Mehrael – OpenAI integration: review summarizer + route optimizer + AI recommendation API - Mahmoud – Anti-Scam Assistant page + price-warning UI + negotiation phrases section - Basmala – Route With Soul: cultural route renderer on map + Memory Map shareable page - Kirls – QA: test AI features and maps; accessibility audit on all pages built so far | - AI-powered review summaries working - Route With Soul functional on map - Memory Map shareable link generated |
| Week 6 (Mar 8–14) | - Gerges – Design Admin Dashboard, multi-language toggle UI, and Accessibility Mode screens - Eman – Multi-language support backend logic + Arabic/English content API - Mehrael – Admin Dashboard API: manage places, guides, and reviews with moderation - Mahmoud – Admin Dashboard React pages + Accessibility Mode frontend - Basmala – Multi-language toggle integration across all pages (AR/EN switch) - Kirls – Final UI polish pass, responsive QA across mobile/tablet/desktop | - Bilingual (AR/EN) site working - Admin Dashboard operational - All modules integrated and tested |
| Week 7 (Mar 15–21) | - Gerges – Prepare final Figma handoff file and all exported design assets - Eman – Deploy backend to Render/Railway; configure environment variables and CORS - Mehrael – Performance optimization, security hardening, rate limiting on all APIs - Mahmoud – Deploy frontend to Vercel; configure production environment - Basmala – End-to-end integration testing across all modules on production - Kirls – Write README, full API docs (Postman collection), and user guide | - Live deployed application (public URL) - Full API documentation (Postman collection) - Project README and user guide complete |
| Week 8 (Mar 22–31) | - Gerges – Design presentation slides and final demo screens - Eman – Fix all critical bugs found during final testing - Mehrael – Final backend stress testing and bug fixes - Mahmoud – Fix all frontend UI bugs and polish interactions - Basmala – User acceptance testing with real test users; collect feedback - Kirls – Prepare demo script, walkthrough plan, and final report draft | - Demo-ready application on production - Graduation project presentation slides - Final report first draft submitted |
| April – May (Supervisor Review) | - All team – Address all supervisor feedback from Week 8 review - Eman & Mehrael – Add stretch features: push notifications, advanced AI recommendations - Gerges – Update design assets based on feedback - Mahmoud & Basmala – Frontend refinements based on user testing results - Kirls – Finalize complete project documentation and defense preparation | - All supervisor feedback addressed - Stretch features implemented (if time permits) - Defense preparation materials ready |
| June (Final Submission) | - All team – Final code freeze and last review - Kirls – Submit final project report and all documentation - All team – Graduation project defense presentation | - Final report submitted - Source code archived on GitHub - Graduation project defense completed |

# 8. Expected Impact

- Improve Egypt's image as a modern, tourist-friendly digital destination.

- Reduce tourist fear, confusion, and vulnerability to scams.

- Promote authentic Egyptian culture beyond commercial tourist traps.

- Provide licensed tour guides with fair digital opportunities and visibility.

- Increase tourist confidence in planning and navigating Egypt independently.

- Serve as a scalable foundation for future government or private-sector tourism apps.

Project Plan

# 1. Timeline

# 2. Project Milestones

The project is divided into five major milestones, each representing a significant stage in the system development lifecycle. These milestones ensure structured progress, continuous evaluation, and timely delivery.

Milestone 1: Initialization & Design (Weeks 1–2)

- Wireframes and design system

- Database schema

- GitHub setup

- Authentication system

- Basic Places API

Milestone 2: Core Development (Weeks 3–4)

- Trip Planner (end-to-end)

- Places Explorer (dynamic)

- Guide Marketplace (listing & profiles)

- Booking system (basic)

- Chat prototype

Milestone 3: Advanced Features (Weeks 5–6)

- Anti-Scam Assistant

- Route With Soul

- Smart Audio Guide

- AI features (summarization, routing)

- Multi-language (AR/EN)

- Admin Dashboard

Milestone 4: Deployment & Testing (Weeks 7–8)

- Full system integration

- Deployment (Frontend & Backend)

- Testing and bug fixing

- API documentation

- Demo-ready system

Milestone 5: Finalization (April–June)

- Performance optimization

- UI/UX improvements

- Final report

- Presentation and demo

# 3. Deliverables

Technical:

- Web application (Frontend + Backend)

- REST APIs with authentication

- Database (MongoDB)

- Admin dashboard

- AI features

- Real-time chat

Design:

- Wireframes and UI prototypes

- Design system

Documentation:

- Proposal / SRS

- Architecture diagrams

- API documentation

- User guide

- Final report

Deployment:

- Live application (URL)

- GitHub repository

Presentation:

- Slides

- Demo scenario

# 3. Resource Allocation

Gerges (UI/UX): Design system, wireframes, UX
Eman (Full-Stack): Core backend, APIs, integration
Mehrael (Backend & AI): APIs, AI features, security
Mahmoud (Frontend): Marketplace & Admin UI
Basmala (Frontend): Trip Planner & Places Explorer
Kerolles (QA & Docs): Testing, documentation, reporting

Work Distribution:

- Frontend: 50%

- Backend: 30%

- AI: 10%

- QA & Documentation: 10%

Methodology:
Agile development with weekly sprints, GitHub version control, and continuous testing.

Task Assignment & Roles

The following defines each team member role and primary responsibilities throughout the project.

| 1 | Eman | Full-Stack Developer – Backend & Frontend Integration |
| --- | --- | --- |
| 2 | Basmala | Frontend Developer – Pages, Components & Maps UI |
| 3 | Gerges | UI/UX Designer – Wireframes, Prototypes & Design System |
| 4 | Mahmoud | Frontend Developer – Marketplace, Dashboard & Admin UI |
| 5 | Mehrael | Backend Developer – APIs, AI Integration & Security |
| 6 | Kirolos | QA & Documentation – Testing, API Docs & Project Report |

1  Detailed Task Breakdown per Member

| Eman Full-Stack Developer |  |
| --- | --- |
| 1 | Set up Node.js / Express project structure, environment config, and MongoDB Atlas connection |
| 2 | Build Auth API: register, login, JWT token generation, middleware, and role-based access control |
| 3 | Build Trip Planner API: geo-sort algorithm, budget filtering, and cost estimation logic |
| 4 | Build Smart Audio Guide API: proximity trigger logic and audio content endpoints |
| 5 | Integrate multi-language support backend logic (Arabic / English content API) |
| 6 | Deploy backend to Render/Railway and configure production environment variables |
| 7 | Connect React frontend to backend APIs for Trip Planner and Audio Guide modules |
| 8 | Fix all critical bugs identified during final testing phase |

| Basmala Frontend Developer |  |
| --- | --- |
| 1 | Build Homepage layout, hero section, and main navigation using Bootstrap 5 |
| 2 | Build Places Explorer page: static UI cards, filters, and detail page layout |
| 3 | Connect Places Explorer to backend API: dynamic cards, search, and filters |
| 4 | Build Trip Planner frontend: form, interest/budget filters, and results with map pins |
| 5 | Build Route With Soul page: cultural route renderer integrated with Google Maps / Leaflet |
| 6 | Build Memory Map page: post-trip visited places with shareable link generation |
| 7 | Integrate Arabic / English language toggle across all pages |
| 8 | Run user acceptance testing with real users and collect feedback for final fixes |

| Gerges UI/UX Designer |  |
| --- | --- |
| 1 | Define the full design system: color palette, typography, spacing, and component library in Figma |
| 2 | Create low-fidelity wireframes for all main pages (Home, Planner, Explorer, Marketplace, Emergency) |
| 3 | Create high-fidelity mockups and interactive prototype for all screens |
| 4 | Design Trip Planner, Places cards, cultural tips modal, and map view layouts |
| 5 | Design Guide Marketplace pages, booking flow, and in-app chat interface |
| 6 | Design Smart Audio Guide, Route With Soul, Memory Map, and Accessibility Mode screens |
| 7 | Design Admin Dashboard, multi-language toggle UI, and all remaining screens |
| 8 | Prepare final Figma handoff file with all exported assets for developers |

| Mahmoud Frontend Developer |  |
| --- | --- |
| 1 | Set up React project, React Router routing, Redux Toolkit store, and Bootstrap layout |
| 2 | Build Auth pages: Login, Register, and protected route wrappers |
| 3 | Build Guide Marketplace page: guide listing, filter panel, guide profile, and booking form |
| 4 | Build in-app chat UI, booking confirmation, and booking success pages |
| 5 | Build Anti-Scam Assistant page: price-warning components and negotiation phrases section |
| 6 | Build Admin Dashboard React pages: manage places, guides, reviews, and moderation |
| 7 | Build Accessibility Mode frontend: wheelchair-friendly filters and low-crowd route UI |
| 8 | Deploy frontend to Vercel and configure production build settings |

| Mehrael Backend Developer |  |
| --- | --- |
| 1 | Research Egyptian places data sources, scam patterns per city, and emergency contact data |
| 2 | Build Places model, CRUD API endpoints, and seed initial places and cultural tips data |
| 3 | Build Guide model, Marketplace API (list, filter, book), and availability calendar logic |
| 4 | Build Emergency Companion API: hospitals, police, and embassies data per city |
| 5 | Build Booking API and Socket.io real-time chat backend (tourist and guide) |
| 6 | Integrate OpenAI API: review summarizer, route optimizer, and AI recommendation endpoints |
| 7 | Build Admin Dashboard API: manage places, guides, and reviews with moderation logic |
| 8 | Performance optimization, security hardening, rate limiting, and backend stress testing |

| Kirolos QA & Documentation |  |
| --- | --- |
| 1 | Set up GitHub repository, define branching strategy (main / dev / feature branches), manage PRs |
| 2 | Set up Postman collection and document all planned API endpoints from Week 1 |
| 3 | Test Trip Planner and Places Explorer flows; log all bugs on GitHub Issues |
| 4 | Test Guide Marketplace booking flow and in-app chat; update Postman API documentation |
| 5 | Run full accessibility audit across all pages; log and track all issues |
| 6 | Final UI polish pass: responsive QA across mobile, tablet, and desktop breakpoints |
| 7 | Write full README, API documentation (Postman collection export), and user guide |
| 8 | Prepare demo script, walkthrough plan, and final project report draft for submission |

Risk Assessment

# 1. Overview

This document presents a structured risk assessment for the Rafiq graduation project. It identifies 12 risks across four categories — Technical, Business, Legal, and Data — scored by probability and impact, with concrete mitigation strategies for each.

Risk scoring follows a 5×5 matrix:

- Probability: 1 (very unlikely) to 5 (very likely)

- Impact: 1 (minor) to 5 (critical)

- Risk Score = Probability x Impact (max 25)

- High: Score 15–25   Medium: Score 8–14   Low: Score 1–7

# 2. Risk Summary

The table below provides a consolidated view of all identified risks sorted by severity.

| ID | Risk Title | Category | Level | Prob | Impact | Score |
| --- | --- | --- | --- | --- | --- | --- |
| R01 | Guide verification & trust fraud | business | HIGH | 4 | 5 | 20/25 |
| R02 | Inaccurate pricing data | data | HIGH | 4 | 4 | 16/25 |
| R03 | Low user adoption | business | HIGH | 4 | 5 | 20/25 |
| R04 | Trip Planner AI hallucinations | technical | HIGH | 3 | 5 | 15/25 |
| R05 | Database content gaps | data | MEDIUM | 3 | 4 | 12/25 |
| R06 | Scalability at peak tourist season | technical | MEDIUM | 3 | 4 | 12/25 |
| R07 | Payment & booking security | legal | MEDIUM | 2 | 5 | 10/25 |
| R08 | User-generated review abuse | business | MEDIUM | 4 | 3 | 12/25 |
| R09 | GDPR / data privacy compliance | legal | MEDIUM | 2 | 4 | 8/25 |
| R10 | Audio guide licensing | legal | LOW | 2 | 3 | 6/25 |
| R11 | Scope creep & timeline overrun | business | LOW | 4 | 3 | 12/25 |
| R12 | Multilingual content quality | data | LOW | 2 | 2 | 4/25 |

4 high-priority risks require immediate attention in the architecture and design phases. 5 medium risks should be addressed before launch. 3 low risks can be monitored and deferred to post-launch iterations.

# 3. Detailed Risk Analysis

Each risk is analyzed with its description and recommended mitigation strategy.

| R01 Guide verification & trust fraud |  |  |  |
| --- | --- | --- | --- |
| Level: HIGH | Category: Business | Probability: 4/5 Impact: 5/5 | Risk Score: 20/25 |
| Risk Description |  | Mitigation Strategy |  |
| Fake or unqualified tour guides register on the marketplace, leading to tourist complaints or safety incidents. |  | Require official Egyptian Tourism Authority (ETA) license uploads. Manual admin review + photo ID matching. Pilot with small verified batch before open registration. |  |

| R02 Inaccurate pricing data |  |  |  |
| --- | --- | --- | --- |
| Level: HIGH | Category: Data | Probability: 4/5 Impact: 4/5 | Risk Score: 16/25 |
| Risk Description |  | Mitigation Strategy |  |
| Anti-Scam Assistant shows outdated prices, destroying user trust if tourists rely on wrong data. |  | Crowdsource price reports with timestamps. Flag stale data (>30 days) visually. Partner with local vendors for verified price feeds over time. |  |

| R03 Low user adoption |  |  |  |
| --- | --- | --- | --- |
| Level: HIGH | Category: Business | Probability: 4/5 Impact: 5/5 | Risk Score: 20/25 |
| Risk Description |  | Mitigation Strategy |  |
| Tourists discover Rafiq too late (after arriving) or prefer existing tools like Google Maps / TripAdvisor. |  | SEO-optimize for pre-trip planning queries. Integrate with travel booking platforms. Add shareable itineraries to drive organic reach. |  |

| R04 Trip Planner AI hallucinations |  |  |  |
| --- | --- | --- | --- |
| Level: HIGH | Category: Technical | Probability: 3/5 Impact: 5/5 | Risk Score: 15/25 |
| Risk Description |  | Mitigation Strategy |  |
| AI-generated schedules suggest closed attractions, wrong opening hours, or geographically impossible routes. |  | Ground AI with structured database (not free-form generation). Validate all suggestions against Places DB before rendering. Add user-editable override. |  |

| R05 Database content gaps |  |  |  |
| --- | --- | --- | --- |
| Level: MEDIUM | Category: Data | Probability: 3/5 Impact: 4/5 | Risk Score: 12/25 |
| Risk Description |  | Mitigation Strategy |  |
| Places Explorer lacks coverage for smaller cities (Siwa, Dahab, etc.), reducing value for off-the-beaten-path tourists. |  | Start with top-20 destinations. Build admin CMS for content team. Allow guide-submitted place listings with moderation queue. |  |

| R06 Scalability at peak tourist season |  |  |  |
| --- | --- | --- | --- |
| Level: MEDIUM | Category: Technical | Probability: 3/5 Impact: 4/5 | Risk Score: 12/25 |
| Risk Description |  | Mitigation Strategy |  |
| System overloads during peak months (October-April), causing slow load times or downtime. |  | Deploy on cloud with auto-scaling (AWS/GCP). Use CDN for static assets. Load test before tourist season launch. |  |

| R07 Payment & booking security |  |  |  |
| --- | --- | --- | --- |
| Level: MEDIUM | Category: Legal | Probability: 2/5 Impact: 5/5 | Risk Score: 10/25 |
| Risk Description |  | Mitigation Strategy |  |
| Guide booking payments are intercepted or disputed, creating liability and user distrust. |  | Use Stripe or Paymob for PCI-compliant payments. Escrow model: release to guide after trip confirmation. Define clear refund policy. |  |

| R08 User-generated review abuse |  |  |  |
| --- | --- | --- | --- |
| Level: MEDIUM | Category: Business | Probability: 4/5 Impact: 3/5 | Risk Score: 12/25 |
| Risk Description |  | Mitigation Strategy |  |
| Guides or competitors post fake reviews, distorting ratings and misleading tourists. |  | Rate-limit reviews per verified booking only. NLP flag for suspicious patterns. Manual moderation escalation path. |  |

| R09 GDPR / data privacy compliance |  |  |  |
| --- | --- | --- | --- |
| Level: MEDIUM | Category: Legal | Probability: 2/5 Impact: 4/5 | Risk Score: 8/25 |
| Risk Description |  | Mitigation Strategy |  |
| Storing tourist location and personal data without proper consent flows triggers legal risk, especially for EU visitors. |  | Add cookie consent banner, privacy policy, and data export/delete endpoints. Minimize data retention. Consult a legal advisor before launch. |  |

| R10 Audio guide licensing |  |  |  |
| --- | --- | --- | --- |
| Level: LOW | Category: Legal | Probability: 2/5 Impact: 3/5 | Risk Score: 6/25 |
| Risk Description |  | Mitigation Strategy |  |
| Audio content narrating historical sites may require approval from Egyptian authorities or historians. |  | Source narration from public domain or original team writing. Consult Ministry of Tourism guidelines. Start with text-only, add audio post-launch. |  |

| R11 Scope creep & timeline overrun |  |  |  |
| --- | --- | --- | --- |
| Level: LOW | Category: Business | Probability: 4/5 Impact: 3/5 | Risk Score: 12/25 |
| Risk Description |  | Mitigation Strategy |  |
| 12 features for a 6-person team across 3 months is ambitious. Over-building risks missing the July deadline. |  | Prioritize MVP: Trip Planner + Places Explorer + Guide Marketplace. Mark remaining features as v2. Use weekly sprint reviews to cut scope early. |  |

| R12 Multilingual content quality |  |  |  |
| --- | --- | --- | --- |
| Level: LOW | Category: Data | Probability: 2/5 Impact: 2/5 | Risk Score: 4/25 |
| Risk Description |  | Mitigation Strategy |  |
| Machine-translated Arabic content contains cultural or linguistic errors that damage credibility. |  | Human review all Arabic UI strings. Use native speakers for content. English-first MVP, Arabic after validation. |  |

# 4. Key Recommendations

## 4.1  Immediate actions (before development starts)

- Define MVP scope: Trip Planner + Places Explorer + Guide Marketplace only. Defer all other features to v2.

- Design the guide verification workflow and required documentation from day one (R01).

- Establish the Places database schema before building the AI Trip Planner to avoid hallucination risks (R04).

## 4.2  Pre-launch checklist

- Integrate a PCI-compliant payment provider (Stripe or Paymob) for guide bookings (R07).

- Add privacy policy, cookie consent, and data deletion endpoints for GDPR compliance (R09).

- Conduct load testing before public launch to validate scalability under peak-season traffic (R06).

## 4.3  Ongoing monitoring

- Set up a pricing data freshness dashboard — flag entries older than 30 days (R02).

- Monitor review submission patterns for anomalies to detect fake review campaigns (R08).

- Track feature completion weekly against the July 2026 deadline and cut scope proactively (R11).

5. Key Performance Indicators (KPIs)

This section defines the quantitative and qualitative metrics used to evaluate the success and operational health of the Rafiq system. These KPIs ensure the project meets its technical, business, and legal objectives while maintaining high data quality.

5.1 KPI Executive Summary

| ID | KPI Name | Category | Target |
| --- | --- | --- | --- |
| KPI01 | Response Time | Technical | < 2 seconds |
| KPI02 | System Uptime | Technical | ≥ 99.5% |
| KPI03 | User Adoption Rate | Business | 10–15% monthly growth |
| KPI04 | DAU / MAU Ratio | Business | ≥ 20% |
| KPI05 | Pricing Data Freshness | Data | 90% within 30 days |
| KPI06 | Content Coverage | Data | 80% of destinations |
| KPI07 | Verified Guides Ratio | Business | 100% verified |
| KPI08 | Booking Conversion Rate | Business | 5–10% |
| KPI09 | Payment Success Rate | Legal / Technical | ≥ 98% |
| KPI10 | User Rating | Business | ≥ 4.2 / 5 |
| KPI11 | Privacy Compliance | Legal | 100% compliance |

5.2 Detailed KPI Analysis

Technical Excellence

• KPI01 - Response Time: Measures system speed to ensure a seamless experience, particularly for the AI Trip Planner.

• KPI02 - System Uptime: Monitors the availability of services to ensure reliability during peak Egyptian tourist seasons.

Business Growth & Engagement

• KPI03 - User Adoption Rate: Tracks the effectiveness of marketing and organic reach in attracting new tourists monthly.

• KPI04 - DAU / MAU Ratio: Evaluates user retention and how often the app is used as a daily companion during trips.

Data Quality & Integrity

• KPI05 - Pricing Data Freshness: Ensures Anti-Scam Assistant accuracy.

• KPI06 - Content Coverage: Quantifies Places Explorer database depth.

5.3 Monitoring & Corrective Actions

All KPIs are tracked via internal real-time dashboards. Any metric falling below the established target threshold will trigger immediate corrective actions to restore system performance and maintain user trust.

Rafiq The intelligent, human-centered bridge between Egypt and its visitors — combining technology, culture, and safety in one unified platform.